## Scope & Sources
cmsdk_apb_watchdog Verification Testplan -- Scope & Sources
DUT | cmsdk_apb_watchdog.v (top) + cmsdk_apb_watchdog_frc.v (free-running counter core)
RTL sources reviewed | cmsdk/logical/cmsdk_apb_watchdog/verilog/cmsdk_apb_watchdog.v, cmsdk_apb_watchdog_frc.v, cmsdk_apb_watchdog_defs.v
Spec reviewed | DDI0479D_m_class_processor_system_r1p1_trm (2).pdf -- actually the Arm Cortex-M System Design Kit TRM; Section 4.5 'APB watchdog' (pages 4-20..4-31), plus Chapter 1 revision history and Appendix C.
Planned verification architecture | 2 agents (APB, WDOG pin-level) + reference model (time-evolving, tracks CDC pending-load/pending-clear state) + scoreboard (queue/transaction-level matching), supplemented with SVA assertions for protocol compliance and local structural invariants (lock gating, ITCR bypass mux, RIS->MIS->RES implication chain). See prior discussion in this session for the full RM+SB vs. assertions rationale.
Out of scope (flagged, not covered) | SoC-level WDOGRES/WDOGINT consumption (reset generator, NMI wiring); UPF/power-aware simulation; bus-fabric-level PSTRB/byte-lane handling upstream of this slave. See Open Questions sheet.
Open items | 7 items requiring a ruling from the design/verification lead before implementation -- see 'Open Questions' sheet.
Test count | 86 test cases across 15 categories.

## Testplan
Test ID | Category | Feature | Scenario | Description / Stimulus | Expected Result | Check Method | Test Type | Priority | TRM / RTL Reference | Status
WDOG_RST_01 | Reset & Default State | PRESETn | WDOGLOAD reset value | Assert then deassert PRESETn with no prior writes. | WDOGLOAD reads 0xFFFFFFFF. | RM+SB | Functional | P0 | TRM Table 4-17; RTL wdog_load reset | Not Started
WDOG_RST_02 | Reset & Default State | PRESETn | WDOGVALUE reset value | Read WDOGVALUE immediately after reset, before any WDOGCLK edge. | WDOGVALUE reads 0xFFFFFFFF. | RM+SB | Functional | P0 | TRM Table 4-17; RTL reg_count reset | Not Started
WDOG_RST_03 | Reset & Default State | PRESETn | WDOGCONTROL reset value | Read WDOGCONTROL after reset. | INTEN=0, RESEN=0; counter disabled, no interrupt/reset possible. | RM+SB | Functional | P0 | TRM Table 4-17 | Not Started
WDOG_RST_04 | Reset & Default State | PRESETn | WDOGRIS / WDOGMIS reset value | Read WDOGRIS and WDOGMIS after reset. | Both read 0x0. | RM+SB | Functional | P0 | TRM Table 4-17 | Not Started
WDOG_RST_05 | Reset & Default State | PRESETn | WDOGLOCK reset value | Read WDOGLOCK after reset. | Reads 0x0 (unlocked, write access enabled). | RM+SB | Functional | P0 | TRM Table 4-17; RTL wdog_lock<=0 | Not Started
WDOG_RST_06 | Reset & Default State | PRESETn | WDOGITCR reset value | Read WDOGITCR after reset. | Reads 0x0 (integration test mode disabled). | RM+SB | Functional | P1 | TRM Table 4-17 | Not Started
WDOG_RST_07 | Reset & Default State | PRESETn | Output pins at reset | Sample WDOGINT/WDOGRES immediately after PRESETn deassert, before any WDOGCLK edge. | Both LOW. | Assertion | Functional | P0 | RTL top-level mux | Not Started
WDOG_RST_08 | Reset & Default State | WDOGRESn | Independent reset domains | Exercise PRESETn and WDOGRESn independently and simultaneously: (a) PRESETn only, (b) WDOGRESn only, (c) both together, (d) staggered de-assertion. | PCLK-domain regs (LOCK/ITCR/ITOP/CONTROL/LOAD) reset only on PRESETn; WDOGCLK-domain state (reg_count, wdog_ris, i_wdog_res, reg_carry, toggle sync flops) resets only on WDOGRESn. No X-propagation either way. | RM+SB + Assertion | Corner | P0 | RTL: two async resets, PRESETn vs WDOGRESn | Not Started
WDOG_RST_09 | Reset & Default State | WDOGRESn | Reset during active operation | Assert reset while counter running, interrupt latched, and/or a load or int-clear toggle-sync request mid-flight. | Clean recovery to reset defaults; pending toggle-sync requests (load_req_tog, int_clr_tog) do not replay a stale load/clear after reset deasserts. | RM+SB | Corner | P1 | RTL CDC toggle sync state | Not Started
WDOG_REG_01 | Register Access | Word access | Basic write/readback data integrity | Write walking-1s, walking-0s, all-0, all-1, and random patterns to WDOGLOAD; read back. | Readback matches last written value exactly. | RM+SB | Functional | P0 | TRM WDOGLOAD | Not Started
WDOG_REG_02 | Register Access | Memory map | Full register map sweep | Read every address in TRM Table 4-17 after reset and after programming known values. | Each register returns its documented reset/programmed value. | RM+SB | Functional | P0 | TRM Table 4-17 | Not Started
WDOG_REG_03 | Register Access | Memory map | Unmapped address read/write | Access addresses inside the 4KB APB region not listed in Table 4-17. | Reads return 0x0; writes have no effect on any register. | RM+SB | Negative | P1 | RTL prdata_next default terms | Not Started
WDOG_REG_04 | Register Access | Reserved bits | Reserved bits read as zero | Write 0xFFFFFFFF to WDOGCONTROL, WDOGRIS(n/a,RO), WDOGMIS(RO), WDOGITCR, WDOGITOP; read back. | Reserved bit positions ([31:2] CONTROL/ITOP, [31:1] RIS/MIS/ITCR) always read 0. | Assertion | Functional | P0 | TRM Figures 4-16/4-17/4-18/4-20/4-21 | Not Started
WDOG_REG_05 | Register Access | WDOGINTCLR | Write-only register read | Read from the WDOGINTCLR address. | Returns 0x0; no side effect (interrupt state / counter unaffected by the read). | RM+SB | Negative | P1 | RTL frc_data default case (WDOGINTCLR not in read mux) | Not Started
WDOG_REG_06 | Register Access | Peripheral ID | ECOREVNUM reflection | Sweep ECOREVNUM[3:0] across all 16 values; read WDOGPERIPHID3. | WDOGPERIPHID3[7:4] == ECOREVNUM; [3:0] fixed at 0x0. | RM+SB | Functional | P2 | TRM Table 4-17 WDOGPERIPHID3; RTL ECOREVNUM port | Not Started
WDOG_REG_07 | Register Access | Peripheral / PrimeCell ID | Fixed ID constants | Read WDOGPERIPHID0/1/2/4/5/6/7 and WDOGPCELLID0/1/2/3. | Match fixed values in TRM Table 4-17 (e.g. PERIPHID0=0x24, PCELLID0=0x0D, etc.). | RM+SB | Functional | P2 | TRM Table 4-17 | Not Started
WDOG_LOCK_01 | Lock Mechanism | WDOGLOCK | Default unlocked state | After reset, write to WDOGLOAD/CONTROL/INTCLR without touching WDOGLOCK. | Writes succeed (device is unlocked by default). | RM+SB | Functional | P0 | TRM WDOGLOCK reset=0x0 | Not Started
WDOG_LOCK_02 | Lock Mechanism | WDOGLOCK | Unlock with magic value | Write 0x1ACCE551 to WDOGLOCK. | WDOGLOCK reads back 0x0 (unlocked); subsequent register writes succeed. | RM+SB | Functional | P0 | TRM WDOGLOCK bit[0]; RTL wdog_lock_wr_val | Not Started
WDOG_LOCK_03 | Lock Mechanism | WDOGLOCK | Lock with any non-magic value | Write several non-magic values (0x0, 0xFFFFFFFF, 0x1ACCE550, 0x1ACCE552) to WDOGLOCK. | WDOGLOCK reads back 0x1 (locked) in every case; subsequent writes to LOAD/CONTROL/INTCLR/ITCR/ITOP are ignored (values unchanged). | RM+SB | Functional + Negative | P0 | TRM WDOGLOCK; RTL wdog_lock_wr_val default=1 | Not Started
WDOG_LOCK_04 | Lock Mechanism | WDOGLOCK | Locked WDOGINTCLR is ignored | Latch an interrupt, lock the device, then write WDOGINTCLR. | Interrupt remains latched (WDOGRIS/WDOGMIS unchanged) and counter is NOT reloaded. | RM+SB | Negative | P0 | RTL int_clr_en includes ~wdog_lock | Not Started
WDOG_LOCK_05 | Lock Mechanism | WDOGLOCK | WDOGLOCK itself is never gated | Lock the device, then write 0x1ACCE551 to WDOGLOCK again. | Unlock succeeds even while currently locked (WDOGLOCK write path has no dependency on current lock state). | RM+SB | Functional | P0 | RTL wdog_lock_wr_en has no wdog_lock term | Not Started
WDOG_LOCK_06 | Lock Mechanism | WDOGLOCK | Read masking | Write 0xDEADBEEF and 0x1ACCE551 to WDOGLOCK in turn; read back after each. | Read always returns only bit[0] (0x1 or 0x0), never the raw written value. | RM+SB | Functional | P1 | TRM Fig 4-19 read returns bottom bit only | Not Started
WDOG_LOCK_07 | Lock Mechanism | WDOGLOCK | Lock does not affect free-running counter | Start the counter, then lock the device; let it continue counting. | Counter keeps decrementing normally; only register writes are blocked. | RM+SB | Functional | P1 | RTL: wdog_lock gates *_wr_en only, not the FRC datapath | Not Started
WDOG_LOCK_08 | Lock Mechanism | WDOGLOCK | Locked WDOGITCR/WDOGITOP ignored | Lock the device, then attempt to write WDOGITCR and WDOGITOP. | Both writes ignored; integration test mode cannot be entered while locked. | RM+SB | Negative | P1 | RTL wdog_itcr_wr_en / wdog_itop_wr_en gated by ~wdog_lock | Not Started
WDOG_CTRL_01 | Control Register | INTEN | Counter frozen when disabled | Leave INTEN=0 (default); pulse WDOGCLKEN/WDOGCLK for many cycles. | WDOGVALUE never changes. | RM+SB | Functional | P0 | TRM WDOGCONTROL[0]; RTL count_stop gated by wdog_int_en | Not Started
WDOG_CTRL_02 | Control Register | INTEN | Counter runs when enabled | Set INTEN=1 with WDOGLOAD pre-programmed; apply WDOGCLK/WDOGCLKEN. | Counter decrements by 1 per valid WDOGCLK edge. | RM+SB | Functional | P0 | TRM WDOGCONTROL[0] | Not Started
WDOG_CTRL_03 | Control Register | INTEN | Reload on 0->1 transition | With counter partway through a count (not equal to WDOGLOAD), clear INTEN then set INTEN again. | Counter snaps back to the current WDOGLOAD value on the enable rising edge, not continuing from its old value. | RM+SB | Functional | P1 | RTL wdog_int_en_rise | Not Started
WDOG_CTRL_04 | Control Register | INTEN | Counter freezes on disable | Start counting, disable INTEN mid-count, wait many WDOGCLK edges, re-read WDOGVALUE. | Value is unchanged from the moment INTEN was cleared. | RM+SB | Functional | P0 | RTL count_stop / count_mux2 | Not Started
WDOG_CTRL_05 | Control Register | RESEN | Reset output masked when disabled | RESEN=0, INTEN=1; let counter time out twice without servicing. | WDOGINT asserts and re-asserts as expected, but WDOGRES never asserts. | RM+SB | Negative | P0 | TRM WDOGCONTROL[1] | Not Started
WDOG_CTRL_06 | Control Register | RESEN | RESEN without INTEN cannot reset | RESEN=1, INTEN=0 (counter frozen); wait many cycles. | No interrupt or reset ever occurs since the counter never runs. | RM+SB | Corner | P1 | RTL: reset path requires carry_msb, which needs INTEN driving the counter | Not Started
WDOG_CTRL_07 | Control Register | RESEN | Race: RESEN enabled during expiry cycle | Directed + randomized test toggling RESEN 0->1 precisely on the WDOGCLK cycle where carry_msb pulses with WDOGRIS already latched from a prior unserviced timeout. | Confirm actual DUT behavior (reset asserts or not) against RM prediction; see Open Question OQ-7 on expected/required behavior for this sequence. | RM+SB | Corner / Race | P1 | RTL nxt_wdog_res combinational on wdog_res_en, wdog_ris, carry_msb | Not Started
WDOG_CTRL_08 | Control Register | Reserved bits | WDOGCONTROL reserved bits | Write 0xFFFFFFFF to WDOGCONTROL; read back. | Only bits[1:0] retained; bits[31:2] always read 0. | Assertion | Functional | P1 | RTL wdog_control[1:0] register width | Not Started
WDOG_LOAD_01 | Load / Counter Reload | WDOGLOAD | Immediate readback bypass | While counter is running, write a new value to WDOGLOAD and read WDOGVALUE on the very next APB cycle (before any new WDOGCLK edge can have occurred). | WDOGVALUE already reflects the newly written LOAD value (count_read bypass path), not the pre-write counter value. | RM+SB (live/time-evolving RM) | Functional | P0 | RTL count_read = load_req_w ? wdog_load : reg_count | Not Started
WDOG_LOAD_02 | Load / Counter Reload | WDOGLOAD | Actual counter load across CDC | Write WDOGLOAD, then poll WDOGVALUE across subsequent WDOGCLK edges until the toggle-sync completes. | Counter is loaded with the new value on the WDOGCLK edge following handshake completion, then decrements normally from there. | RM+SB | Functional | P0 | RTL load_req_w toggle synchronizer | Not Started
WDOG_LOAD_03 | Load / Counter Reload | WDOGLOAD | Minimum valid value (=1) | Load WDOGLOAD=0x1, enable counter. | Counter reaches 0 after exactly one qualified WDOGCLK edge; interrupt asserts on schedule. | RM+SB | Functional | P0 | TRM: 'minimum valid value for WDOGLOAD is 1' | Not Started
WDOG_LOAD_04 | Load / Counter Reload | WDOGLOAD | Out-of-spec value (=0) | Load WDOGLOAD=0x0 (below the documented minimum), enable counter. | DUT must not hang, lock up, or produce X/undefined propagation; document actual observed behavior. See Open Question OQ-2 for pass/fail ruling. | RM+SB | Negative / Corner | P2 | TRM: minimum valid value is 1 (0 undocumented) | Not Started
WDOG_LOAD_05 | Load / Counter Reload | WDOGLOAD | Back-to-back loads faster than CDC handshake | Write WDOGLOAD twice (or more) in consecutive APB cycles, faster than the load toggle-sync can complete. | Only the final written value is ultimately loaded into the counter; no corrupted/intermediate load, no missed toggle. | RM+SB | Corner / CDC robustness | P0 | RTL load_tog_en = load_en_reg & ~load_req_w | Not Started
WDOG_LOAD_06 | Load / Counter Reload | WDOGLOAD | Load ignored while locked | Lock device, attempt WDOGLOAD write. | WDOGLOAD register and counter both unchanged. | RM+SB | Negative | P0 | See WDOG_LOCK_03 | Not Started
WDOG_LOAD_07 | Load / Counter Reload | WDOGLOAD | Load restarts counter after reset event | Drive counter to a WDOGRES timeout (count_stop=1), then write a new WDOGLOAD value. | Counter resumes counting from the new value; count_stop clears. | RM+SB | Functional | P1 | RTL count_stop cleared by load_req_w | Not Started
WDOG_CNT_01 | Free-running Counter | Decrement rate | One decrement per qualified edge | Sweep WDOGCLK:PCLK ratios (1:1, 1:2, 1:4, 1:8 via WDOGCLKEN gating patterns). | Counter decrements by exactly 1 per WDOGCLK rising edge where WDOGCLKEN=1, at every ratio. | RM+SB (live RM) | Functional | P0 | TRM Table 4-24 WDOGCLKEN | Not Started
WDOG_CNT_02 | Free-running Counter | WDOGCLKEN | Held low: no decrement | Hold WDOGCLKEN=0 for an extended period while WDOGCLK continues toggling. | Counter value does not change at all. | RM+SB + Assertion | Functional | P0 | TRM: 'counters only decrement on a rising edge of WDOGCLK when WDOGCLKEN is HIGH' | Not Started
WDOG_CNT_03 | Free-running Counter | WDOGCLKEN | Irregular/gapped enable pulses | Randomize WDOGCLKEN gaps; cross-check counter value at random read points. | Counter value always matches RM prediction for the exact number of qualified edges seen. | RM+SB (live RM) | Random | P1 | RTL WDOGCLKEN qualifies all WDOGCLK-domain sequential updates | Not Started
WDOG_CNT_04 | Free-running Counter | Counter datapath | 16-bit half-word carry chain | Directed loads exercising the split-counter carry boundary: 0x00010000, 0x00000001, 0x00008000, 0x0000FFFF, 0xFFFF0001. | Borrow from lower to upper half-word (and resulting carry_msb) behaves correctly at every boundary value. | RM+SB | Corner | P0 | RTL comment: '32 bit counter implemented as two 16 bit counters to improve FPGA implementation' | Not Started
WDOG_CNT_05 | Free-running Counter | Race | Expiry coincides with software LOAD/CLR | Directed + randomized: arrange a WDOGLOAD write or WDOGINTCLR write to land on the exact WDOGCLK edge where the counter naturally reaches 0. | No ambiguous/glitched state; final counter/interrupt/reset state matches RM for whichever event the RTL priority logic resolves to. | RM+SB | Corner / Race | P1 | RTL count_mux1 OR-priority: load_req_w ¦ carry_msb ¦ wdog_int_en_rise ¦ int_clr_w | Not Started
WDOG_CNT_06 | Free-running Counter | WDOGVALUE | Glitch-free live readback | Read WDOGVALUE at many random un-synchronized points while counter is actively running. | Every read returns a self-consistent, monotonically-decrementing value with no garbage/intermediate states. | RM+SB (live RM) | Random | P0 | See prior discussion: live time-evolving RM required | Not Started
WDOG_INT_01 | Interrupt Generation | WDOGRIS/MIS | First timeout asserts interrupt | Counter reaches 0 with INTEN=1. | WDOGRIS=1; WDOGMIS = WDOGRIS & INTEN = 1; WDOGINT pin follows WDOGMIS. | RM+SB | Functional | P0 | TRM WDOGRIS/WDOGMIS definitions | Not Started
WDOG_INT_02 | Interrupt Generation | WDOGRIS/MIS | Interrupt unreachable while disabled | With INTEN=0 (counter frozen), wait many cycles. | WDOGRIS/WDOGMIS/WDOGINT never assert. | Assertion | Negative | P1 | Follows from WDOG_CTRL_01 | Not Started
WDOG_INT_03 | Interrupt Generation | WDOGRIS | Interrupt stays latched | After a timeout, let many further WDOGCLK edges and counter reload/recount cycles pass without writing WDOGINTCLR. | WDOGRIS remains 1 (does not self-clear). | Assertion | Functional | P0 | RTL nxt_wdog_ris = (carry_msb ¦ wdog_ris) & ~int_clr_w | Not Started
WDOG_INT_04 | Interrupt Generation | WDOGMIS | MIS tracks INTEN independent of RIS | With WDOGRIS=1 latched, toggle INTEN: 1->0->1. | WDOGMIS drops to 0 the instant INTEN clears (even though RIS stays 1), and reasserts to 1 immediately when INTEN is set again -- without needing a new timeout. | RM+SB | Functional | P1 | RTL wdog_mis = read_wdog_ris & wdog_int_en | Not Started
WDOG_INT_05 | Interrupt Generation | Periodic behavior | Steady-state serviced interrupts | Run N successive timeout cycles, servicing each with WDOGINTCLR before the next expiry. | Interrupt asserts and clears on schedule every cycle, period matching WDOGLOAD each time; no drift, no missed/spurious events over the soak. | RM+SB | Regression / Soak | P1 | Composite of LOAD/INT/CLR behavior | Not Started
WDOG_CLR_01 | Interrupt Clear | WDOGINTCLR | Clear and reload on write | With an interrupt latched, write WDOGINTCLR (try data=0x0 and data=0xFFFFFFFF -- spec says 'any value'). | WDOGRIS/WDOGMIS/WDOGINT clear to 0; counter reloads from current WDOGLOAD. | RM+SB | Functional | P0 | TRM: 'a write of any value to WDOGINTCLR clears...and reloads' | Not Started
WDOG_CLR_02 | Interrupt Clear | WDOGINTCLR | Unconditional reload even with no pending interrupt | With WDOGRIS=0 (no pending interrupt), write WDOGINTCLR. | No-op on interrupt state, but counter still reloads from WDOGLOAD per spec wording (reload is unconditional, not gated on RIS being set). | RM+SB | Corner | P1 | RTL int_clr_w feeds count_mux1 regardless of wdog_ris | Not Started
WDOG_CLR_03 | Interrupt Clear | WDOGINTCLR | Clear ignored while locked | See WDOG_LOCK_04. | See WDOG_LOCK_04. | RM+SB | Negative | P0 | RTL int_clr_en includes ~wdog_lock | Not Started
WDOG_CLR_04 | Interrupt Clear | WDOGINTCLR | Rapid repeated clears (CDC robustness) | Write WDOGINTCLR multiple times back-to-back, faster than the int-clear toggle-sync can complete. | No double-toggle / missed-clear corruption; final state matches a single logical clear-and-reload. | RM+SB | Corner / CDC robustness | P0 | RTL int_clr_en gated by ~int_clr_w (suppresses re-trigger while pending) | Not Started
WDOG_CLR_05 | Interrupt Clear | WDOGINTCLR | Race with natural expiry | Directed + randomized: write WDOGINTCLR exactly as carry_msb is asserting (counter naturally expiring at the same time). | Deterministic resolution matching RM; no interrupt gets 'stuck' latched or spuriously double-cleared. | RM+SB | Corner / Race | P1 | RTL int_clr_w deasserts on ~carry_msb | Not Started
WDOG_RES_01 | Reset Generation | WDOGRES | First timeout does not reset | First-ever counter expiry since enable/load, RESEN=1. | WDOGINT/WDOGRIS assert, but WDOGRES does NOT assert yet. | RM+SB | Functional | P0 | TRM Fig 4-15 flow diagram | Not Started
WDOG_RES_02 | Reset Generation | WDOGRES | Second unserviced timeout resets | Let the interrupt from the first timeout go unserviced through to a second expiry, RESEN=1. | WDOGRES asserts on the second expiry. | RM+SB | Functional | P0 | TRM: 'if not cleared by the time the counter next reaches 0, reasserts reset'; RTL wdog_ris & carry_msb | Not Started
WDOG_RES_03 | Reset Generation | WDOGRES | Proper servicing avoids reset | Write WDOGINTCLR after the first timeout, before the second expiry. | Second expiry only re-asserts WDOGINT/WDOGRIS; WDOGRES never asserts. | RM+SB | Functional | P0 | RTL: int_clr_w reload clears wdog_ris before next carry_msb | Not Started
WDOG_RES_04 | Reset Generation | WDOGRES | Counter stops after reset assertion | Let WDOGRES assert; observe counter over further WDOGCLK edges without any WDOGLOAD write. | Counter remains stopped (count_stop latched); does not silently resume. | RM+SB | Functional | P0 | RTL count_stop = i_wdog_res ? 1 : ... | Not Started
WDOG_RES_05 | Reset Generation | WDOGRES | Does a LOAD write clear WDOGRES? | After WDOGRES asserts, write a new value to WDOGLOAD (counter resumes counting per WDOG_LOAD_07). Observe the WDOGRES pin itself. | Per RTL, i_wdog_res is a level held by 'wdog_res_en ? ... : i_wdog_res' -- it is NOT cleared by a LOAD write; only clearing RESEN deasserts it. Confirm this is the actual and intended behavior. See Open Question OQ-1. | RM+SB | Corner | P0 | RTL nxt_wdog_res sticky-latch structure | Not Started
WDOG_RES_06 | Reset Generation | WDOGRES | RESEN clear/set clears the sticky latch | With WDOGRES asserted, clear RESEN (CONTROL[1]=0), observe WDOGRES deassert, then set RESEN=1 again with no new qualifying timeout. | WDOGRES deasserts when RESEN clears; does not spuriously reassert merely from RESEN being set again absent a new wdog_ris & carry_msb event. | RM+SB | Functional | P0 | RTL nxt_wdog_res = ~wdog_res_en ? 0 : ... | Not Started
WDOG_RES_07 | Reset Generation | WDOGRES | Pulse width / SoC consumption | N/A at unit level -- flag for SoC integration-level testplan. | Confirm downstream reset generator's required WDOGRES assertion duration; TRM does not specify one at the IP level. See Open Question OQ-6. | Out of scope (unit-level) | N/A | P2 | TRM does not document minimum WDOGRES pulse width | Not Started
WDOG_RES_08 | Reset Generation | WDOGRES | Integration test mode interaction | Start a real countdown toward a reset condition, then enter WDOGITCR=1 mid-sequence (masking WDOGRES with WDOGITOP[0]), then exit test mode. | While ITCR=1, WDOGRES reflects only WDOGITOP[0]; the real i_wdog_res state continues evolving underneath and becomes visible again, correctly, once ITCR clears. | RM+SB | Corner | P1 | RTL top-level output mux: WDOGRES = itcr ? itop[0] : i_wdogres | Not Started
WDOG_ITM_01 | Integration Test Mode | WDOGITCR | Test mode overrides outputs | Set WDOGITCR=1, sweep WDOGITOP[1:0] through all 4 combinations. | WDOGINT == WDOGITOP[1] and WDOGRES == WDOGITOP[0] in every case, regardless of actual counter/interrupt state. | RM+SB + Assertion | Functional | P1 | TRM WDOGITCR/WDOGITOP; RTL output mux | Not Started
WDOG_ITM_02 | Integration Test Mode | WDOGITCR | Exit test mode reverts outputs | From test mode with WDOGITOP forcing known values, clear WDOGITCR=0. | WDOGINT/WDOGRES immediately revert to the real counter-driven (i_wdogint/i_wdogres) values. | RM+SB | Functional | P1 | RTL output mux | Not Started
WDOG_ITM_03 | Integration Test Mode | WDOGITOP | Write independent of mode | Write WDOGITOP while WDOGITCR=0 (test mode not active). | Register write succeeds and is retained, but has no effect on WDOGINT/WDOGRES until WDOGITCR is later set. | RM+SB | Functional | P2 | RTL wdog_itop register vs mux selection | Not Started
WDOG_ITM_04 | Integration Test Mode | Lock interaction | ITCR/ITOP gated by lock | See WDOG_LOCK_08. | See WDOG_LOCK_08. | RM+SB | Negative | P1 | RTL wdog_itcr_wr_en / wdog_itop_wr_en | Not Started
WDOG_ITM_05 | Integration Test Mode | WDOGITOP | Full truth table sweep | Cover all 4 values of WDOGITOP[1:0] while WDOGITCR=1 as an explicit coverage bin. | Each combination maps to the correct WDOGINT/WDOGRES pin state. | Assertion / Coverage | Functional | P2 | RTL output mux | Not Started
WDOG_APB_01 | APB Protocol | Handshake | Standard SETUP/ACCESS access to every register | Drive standard single-cycle APB read and write handshakes (PSEL/PENABLE/PWRITE/PADDR/PWDATA) to each register in the map. | All accesses complete correctly per APB protocol; register decode matches Table 4-17. | Assertion (APB protocol) + RM+SB (data) | Functional | P0 | Standard AMBA APB3 protocol | Not Started
WDOG_APB_02 | APB Protocol | Handshake | Back-to-back transactions | Issue consecutive transactions with no idle cycle between ACCESS phase and next SETUP phase. | No data corruption, no missed writes/reads across the boundary. | RM+SB | Functional | P1 | RTL write decode qualified on PSEL & PWRITE & ~PENABLE | Not Started
WDOG_APB_03 | APB Protocol | Handshake | Write capture timing | Verify exactly which APB cycle a write is captured on relative to the PENABLE transition. | Write is captured at the SETUP->ACCESS boundary (~PENABLE term), consistent with RTL decode logic for every writable register. | Assertion | Functional | P0 | RTL: <reg>_wr_en = ... & (~PENABLE) | Not Started
WDOG_APB_04 | APB Protocol | Bus reuse | Read/write sequencing, no stale data | Interleave reads and writes to different registers back-to-back. | PRDATA never shows stale data from a prior unrelated register access. | RM+SB | Functional | P1 | RTL i_prdata single registered read-data path | Not Started
WDOG_APB_05 | APB Protocol | Slave timing | Zero wait-state slave | Confirm the module has no PREADY/PSLVERR ports -- environment should not attempt to inject wait states or slave errors at this unit level. | Fixed single-cycle response for every access; document as an environment configuration constraint, not a DUT test. | Environment config note | N/A | P2 | RTL port list: no PREADY/PSLVERR | Not Started
WDOG_APB_06 | APB Protocol | Byte lanes | No PSTRB at this sub-block | Confirm the module exposes no PSTRB port; full-word writes only at this interface. | Document scope: byte-lane partial-write handling, if any, must be verified at the bus-fabric/wrapper level, not here. See Open Question OQ-4. | Out of scope (unit-level) | N/A | P2 | RTL port list: no PSTRB | Not Started
WDOG_CDC_01 | Clock Domain Crossing | Clock ratio | Sweep WDOGCLK:PCLK ratios | Run the full functional suite at multiple WDOGCLK:PCLK relationships realized via WDOGCLKEN gating (e.g. 1:1, 1:2, 1:4, 1:8). | Load/clear/count/interrupt/reset behavior is correct at every ratio tested. | RM+SB (live RM) | Functional | P0 | TRM: 'WDOGCLK must be synchronous to PCLK' | Not Started
WDOG_CDC_02 | Clock Domain Crossing | Stalled WDOGCLK | WDOGCLK stopped while APB active | Hold WDOGCLKEN permanently low (or WDOGCLK not toggling) while issuing APB writes to WDOGLOAD/CONTROL/WDOGINTCLR. | PCLK-domain register writes still complete; pending load/clear toggle requests remain queued and apply correctly once WDOGCLK resumes -- nothing is silently lost. | RM+SB | Corner | P0 | RTL toggle-based load_req_w / int_clr_w handshake | Not Started
WDOG_CDC_03 | Clock Domain Crossing | Independent resets | PRESETn / WDOGRESn skew | Cross-reference WDOG_RST_08. | Cross-reference WDOG_RST_08. | RM+SB + Assertion | Corner | P0 | RTL two async reset domains | Not Started
WDOG_CDC_04 | Clock Domain Crossing | Phase relationship | True-async vs synchronous-ratio WDOGCLK generation | TBD pending Open Question OQ-3: either constrain WDOGCLK generation to integer synchronous ratios of PCLK (per TRM), or additionally stress genuinely random-phase/async WDOGCLK if metastability-class robustness is in scope. | Scope and pass/fail criteria to be confirmed before implementation. | RM+SB | Random | P2 | TRM: 'WDOGCLK must be synchronous to PCLK' | Not Started
WDOG_ERR_01 | Error / Illegal / Corner | Read-only regs | Writes to RO registers are no-ops | Attempt writes to WDOGVALUE, WDOGRIS, WDOGMIS, and all Peripheral/PrimeCell ID registers. | Silently ignored; no register change, no protocol error signaled (module has no PSLVERR). | RM+SB | Negative | P1 | TRM Table 4-17 Type=RO | Not Started
WDOG_ERR_02 | Error / Illegal / Corner | Write-only regs | Read from WDOGINTCLR has no side effect | Cross-reference WDOG_REG_05. | Cross-reference WDOG_REG_05. | RM+SB | Negative | P1 | TRM Table 4-17 Type=WO | Not Started
WDOG_ERR_03 | Error / Illegal / Corner | Address decode | Fully unmapped address space | Cross-reference WDOG_REG_03. | Cross-reference WDOG_REG_03. | RM+SB | Negative | P1 | RTL default decode terms | Not Started
WDOG_ERR_04 | Error / Illegal / Corner | WDOGLOAD | Value below documented minimum | Cross-reference WDOG_LOAD_04. | Cross-reference WDOG_LOAD_04. | RM+SB | Negative / Corner | P2 | TRM minimum valid value note | Not Started
WDOG_ERR_05 | Error / Illegal / Corner | Concurrent channels | LOAD and INTCLR toggle-sync channels overlap | Issue a WDOGLOAD write and a WDOGINTCLR write on consecutive APB cycles so both toggle-sync channels are in flight simultaneously, targeting the shared counter mux. | Both requests are correctly and independently resolved; no cross-channel corruption of the counter value. | RM+SB | Corner | P1 | RTL count_mux1 shared by load_req_w and int_clr_w terms | Not Started
WDOG_PWR_01 | Low Power | Read-data clock gating | r1p0->r1p1 PRDATA ICG transparency | Exercise reads at sparse/idle vs. back-to-back cadence. | PRDATA correctness is unaffected by the read-data-register automatic clock gating introduced in r1p0->r1p1; purely a power optimization, not functionally observable. UPF/power-aware sim scope TBD -- see Open Question OQ-5. | RM+SB | Functional | P2 | TRM Chapter 1 revision history: 'Improved RTL to enable automatic clock gating of read data register' | Not Started
WDOG_RAND_01 | Random / Stress | Full random regression | Constrained-random long-duration soak | Randomize WDOGLOAD values, INTEN/RESEN toggling, WDOGCLKEN gating patterns, WDOGINTCLR timing relative to expiry, lock/unlock sequencing, across many thousands of transactions / timeout cycles. | Zero SB mismatches and zero assertion failures across the full random run; functional coverage closure on all defined bins. | RM+SB + Assertion (queue-based, per earlier arch discussion) | Random | P0 | Composite of all above | Not Started
WDOG_RAND_02 | Random / Stress | Reset injection | Random reset during random activity | Layer random PRESETn / WDOGRESn assertions (independently and jointly) on top of WDOG_RAND_01 traffic. | DUT always recovers cleanly to documented reset defaults; no X-propagation, no stuck/lost toggle-sync state. | RM+SB | Random | P1 | WDOG_RST_08/09 | Not Started

## Open Questions
ID | Question | Why It Matters | Impacted Test IDs | Status
OQ-1 | WDOGRES is implemented as a sticky latch cleared only by de-asserting RESEN (WDOGCONTROL[1]); the TRM does not document how software is expected to clear a reset condition. Is 'toggle RESEN low then high' the intended/only recovery path, or should a fresh WDOGLOAD write also be expected to deassert WDOGRES? | Directly determines pass/fail criteria for WDOG_RES_05/06 and the corresponding RM logic. | WDOG_RES_05, WDOG_RES_06 | Open
OQ-2 | TRM states the minimum valid WDOGLOAD value is 1; RTL does not appear to explicitly reject 0. Is WDOGLOAD=0 formally illegal/UNPREDICTABLE (exclude from functional pass/fail, only check 'does not hang'), or must it produce fully defined behavior? | Determines whether WDOG_LOAD_04/WDOG_ERR_04 are mandatory functional checks or robustness-only checks. | WDOG_LOAD_04, WDOG_ERR_04 | Open
OQ-3 | TRM states WDOGCLK 'must be synchronous to PCLK'. Should the environment only generate WDOGCLK as an integer-ratio, phase-related clock (matching intended use), or should it additionally stress genuinely asynchronous/random-phase WDOGCLK to hunt for metastability-class bugs in the toggle synchronizers, possibly warranting a separate CDC/formal (e.g. Spyglass-CDC style) pass rather than pure functional sim? | Changes scope of WDOG_CDC_04 and whether a dedicated CDC-formal workstream is needed alongside this functional testplan. | WDOG_CDC_01, WDOG_CDC_04 | Open
OQ-4 | This module has no PSTRB port, so it only supports full 32-bit word writes at this interface. Is partial/byte-lane write behavior ever exercised system-wide (i.e. does the upstream bus fabric handle/reject byte writes before they reach this slave), and if so, does that belong in this unit-level testplan or a separate system/integration-level plan? | Determines whether WDOG_APB_06 needs any DUT-level coverage or is purely a scope note. | WDOG_APB_06 | Open
OQ-5 | Is power-aware (UPF) verification of the r1p0->r1p1 automatic read-data-register clock gating in scope for this testplan, or is this purely an RTL functional testplan with power/UPF handled by a separate flow? | Determines whether WDOG_PWR_01 needs a UPF-enabled simulation environment or is satisfied by ordinary functional sim. | WDOG_PWR_01 | Open
OQ-6 | The TRM does not specify a minimum required WDOGRES assertion pulse width for correct system-level reset-generator response. Should this unit-level testplan simply document WDOGRES timing characteristics for the SoC integration team, or is downstream WDOGRES/NMI consumption (per the TRM's example system, where watchdog interrupt ties to processor NMI) expected to be verified here as well? | Clarifies the boundary between this IP's unit-level testplan and SoC-level (m3ds_user_partition / beetle_sysctrl) integration verification. | WDOG_RES_07 | Open
OQ-7 | WDOG_CTRL_07 covers a race where RESEN is enabled on the exact WDOGCLK cycle carry_msb pulses with WDOGRIS already latched. Is toggling RESEN mid-countdown a realistically reachable firmware sequence (vs. RESEN being set once at init and left alone), and if not, should this race be down-prioritized from a mandatory directed test to a random-only / best-effort coverage item? | Affects test prioritization and effort allocation for a scenario whose real-world likelihood is unclear. | WDOG_CTRL_07 | Open

## Register Map (Ref)
Name | Offset | Type | Width | Reset Value | Description
WDOGLOAD | 0x000 | RW | 32 | 0xFFFFFFFF | Reload value; write immediately restarts count. Minimum valid value is 1.
WDOGVALUE | 0x004 | RO | 32 | 0xFFFFFFFF | Current decrementing counter value.
WDOGCONTROL | 0x008 | RW | 2 | 0x0 | [1] RESEN, [0] INTEN.
WDOGINTCLR | 0x00C | WO | - | - | Write any value: clears interrupt and reloads counter from WDOGLOAD.
WDOGRIS | 0x010 | RO | 1 | 0x0 | Raw (unmasked) interrupt status.
WDOGMIS | 0x014 | RO | 1 | 0x0 | Masked interrupt status (RIS & INTEN); drives WDOGINT.
WDOGLOCK | 0xC00 | RW | 32 | 0x0 | Write 0x1ACCE551 to unlock; any other value locks. Read returns bit[0] only.
WDOGITCR | 0xF00 | RW | 1 | 0x0 | Integration Test Mode enable.
WDOGITOP | 0xF04 | WO | 2 | 0x0 | [1] forces WDOGINT, [0] forces WDOGRES, when WDOGITCR=1.
WDOGPERIPHID4 | 0xFD0 | RO | 8 | 0x04 | Block count / jep106_c_code.
WDOGPERIPHID5 | 0xFD4 | RO | 8 | 0x00 | Not used.
WDOGPERIPHID6 | 0xFD8 | RO | 8 | 0x00 | Not used.
WDOGPERIPHID7 | 0xFDC | RO | 8 | 0x00 | Not used.
WDOGPERIPHID0 | 0xFE0 | RO | 8 | 0x24 | Part number [7:0].
WDOGPERIPHID1 | 0xFE4 | RO | 8 | 0xB8 | jep106_id[3:0] / Part number [11:8].
WDOGPERIPHID2 | 0xFE8 | RO | 8 | 0x1B | Revision / jedec_used / jep106_id[6:4].
WDOGPERIPHID3 | 0xFEC | RO | 8 | 0x00 | [7:4] ECO revision number (=ECOREVNUM), [3:0] customer mod number.
WDOGPCELLID0 | 0xFF0 | RO | 8 | 0x0D | Component ID 0.
WDOGPCELLID1 | 0xFF4 | RO | 8 | 0xF0 | Component ID 1.
WDOGPCELLID2 | 0xFF8 | RO | 8 | 0x05 | Component ID 2.
WDOGPCELLID3 | 0xFFC | RO | 8 | 0xB1 | Component ID 3.